## Overview
RAID-A in Contract Management
Contract Contact
Contract title: | Name | Reference no:
Designated Contract Manager: | Name | Job title | email | initials
Contract Team
name |  | Job title | email | initials
name |  | Job title | email | initials
name |  | Job title | email | initials
Senior Responsible Officer (SRO) | name | Job title | Contact Details | initials
RAID-A updated | date | Version no
Circulation list
name |  | Job title | email
name |  | Job title | email
name |  | Job title | email
Summary results
The headline RAG ratings will be aggregated from the completed templates
Residual Risk: | low | medium | high | very high
| 1 | 0 | 0 | 0
Assumptions: | low | medium | high | very high
| 1 | 1 | 0 | 0
Issues: | low | medium | high | very high
| 0 | 0 | 0 | 1
Actions: | complete | on track | delayed | missed
| 0 | 1 | 1 | 0

## RACI
Date updated: |  | RACI
RACI ID | Activity The different activity that will take place during the life of the contract | Responsible The person who performs the work. | Accountable The person ultimately accountable for the work or decision being made. | Consulted Anyone who should be consulted with prior to a decision being made and/or the task being completed. | Informed Anyone who must be informed when a decision is made or work is completed.
RA.001
RA.002
RA.003
RA.004
RA.005
RA.006
RA.007
RA.008
RA.009
RA.010
RA.011
RA.012
RA.013
RA.014
RA.015
RA.016
RA.017
RA.018
RA.019
RA.020
RA.021
RA.022
RA.023
RA.024
RA.025
RA.026

## Risk guidance
Risk Guidance to support completion of the Risks Tab
Risk Scoring Matrix | LIKELIHOOD | Probable | 5 | 10 | 15 | 20 | 25
|  | Likely | 4 | 8 | 12 | 16 | 20
|  | Possible | 3 | 6 | 9 | 12 | 15
|  | Unlikely | 2 | 4 | 6 | 8 | 10
|  | Rare | 1 | 2 | 3 | 4 | 5
|  |  | Negligible | Minor | Moderate | Major | Critical
IMPACT
|  |  | level | low | medium | high | very high
Element | Description Guidance
Objective | Describes the objective for the area of business that is being risk assessed and risk managed.
Risk Description | Describes the barriers/events/circumstances that might prevent the objective from being achieved and include the cause and consequence of the risk that is identified.
Inherent Risk | Scores the risk to the achievement of the objective before any mitigating (control) action has been taken to manage it. Impact - An assessment of the consequences of the risk materialising (scored 1-5) Likelihood - An assessment of the probability of a risk materialising (scored 1-5) Overall Score - Impact x LikelihoodRAG status: Very High (20-25), High (13-19), Moderate (5-12), Low (1-4).
Control / Mitigation | Records the mitigation response to, and control measures over, the risk. Only actual measures in place can be used in determining the residual score.
Residual Risk | Scores the risk still remaining to the achievement of the objective after having taken into account the control measures in place. Should be lower than the Inherent Risk score: mitigating actions should not increase the risk to achieving the objective. Impact An assessment of the consequences of the risk materialising (scored 1-5) LikelihoodAn assessment of the probability of a risk materialising (scored 1-5) Overall Score Impact x Likelihood RAG status: Very High (20-25), High (13-19), Moderate (5-12), Low (1-4).
Further Actions Needed | Records further planned controls or mitigating actions still needed to maintain or reduce the risk to an acceptable level. Actions are needed if the Residual Risk remains above the Target Risk score, if being used (see below).
Owner / Action Date | Records the officer tasked with implementing the further action and the date agreed for implementation of that action.
Date Reviewed | Time stamp of the date reviewed.
Risk Mitigation
Decide not to take a risk – AVOID | A decision is made not to take a risk.
Decide to accept the risk - ACCEPT | A decision is taken to accept the risk.
Decide to transfer the risk – SHARE | A decision is taken to transfer the risk (insurance, outsourcing, spreading/sharing etc).
Decide to reduce the risk - REDUCE | A decision is taken to mitigate or reduce the risk, through controls.
Optional Columns
Proximity | Reflects the possible timing of the risk materialising i.e. is the threat / opportunity stronger at a particular time using the scale: Black - Short Term (0-3 Months) Grey - Medium Term (4-12 Months) Blue - Long Term (13 months+)
Target Risk | Records the level of risk which can be tolerated for that business objective and risk. If the Target Risk is lower than the Residual Risk then there must be further actions identified to bring the risk down. If the Residual Risk and Target Risk agree then the “Further Actions” column can read “none”.
Further guidance - Risk Sources
Risk may come from changes or events that are: |  | Or from factors related to:
External Factors |  | Internal Factors
· Technological |  | · Capacity
· Environmental |  | · Capability
· Economic |  | · Affordability
· Political |  | · Priority setting
· Legislative |  | · Lessons learnt
· Regulatory
· Cultural

## Risks
Date updated: |  |  | Inherent Risk |  |  |  | Residual Risk
Risk ID | Objective Business Objective(s) | Risk Description Barrier(s) to delivery / achievement of the objective | Impact | Likely | Overall score | Management Actions Agreed or Taken Mitigations actually in place to address risk (avoid, reduce, accept, share) | Impact | Likely | Overall score | Target / Tolerance | Further Actions Needed Further mitigations required (avoid, reduce, accept, share) | Action Owner/Date SRO and officer tasked with taking the action and target date for action | Proximity | Date Updated | Date Review by SRO | Comments including reason for change of risk rating
R.001 | Illustrative example only: Completion of the review project | Lack of resilience in staff numbers | 1 | 3 | 3 | Reduce: PM to keep others up to date via highlight reports and meetings. Timetable to be used as record of work done so far and as list of tasks to complete next. | 1 | 2 | 2 | 4 | Accept | Project Manager | long term 13+months
R.002
R.003
R.004
R.005

## Assumptions
Date updated: |  | Assumptions
Assumption ID | Assumption Area e.g. finance, schedual, dependency | Assumption Status Open/Closed | Assumption Description | Rating | Owner | Mitigating Actions | Associated Risk | Associated Action
AS.001 |  |  |  | low |  |  | link to risk register | Link to action
AS.002 |  |  |  | medium
AS.003
AS.004
AS.005
AS.006
AS.007
AS.008
AS.009
AS.010
AS.011
AS.012
AS.013
AS.014
AS.015
AS.016
AS.017
AS.018
AS.019
AS.020
AS.021
AS.022
AS.023
AS.024

## Issues
Date updated: |  | Issues Log
Issue ID | Source of information - eg. email, meeting, conversation/verbal instruction | Date Raised | Status open/close | Description Including impact | Owner | Rating (Example) | Action fix, mitigation or escalation | Date Closed | Resulting risk
I.001 |  |  |  | Illustrative example only: Insufficient focus on ongoing quality assurance of providers | JCH | very high | Add to Information pack, specification as to assurance and escalation process/consequences and contract. Consider remedies |  |  | very high
I.002
I.003 | [9 empty] | Low
I.004
I.005 | [9 empty] | Risk
I.006 | [9 empty] | Issue
I.007
I.008 | [9 empty] | Open
I.009 | [9 empty] | Complete
I.010
I.011
I.012
I.013
I.014
I.015
I.016
I.017
I.018
I.019
I.020
I.021
I.022
I.023
I.024
I.025
I.026
I.027
I.028
I.029
I.030
I.031

## Decision Log
Date updated: |  | Decision Log
Ref | Source of information e.g. email, meeting note, including who requested the decision | Date Raised | Status open or closed | Due Date | Description | Decision Maker Individual or group | Decision / Answer | Decision Date
D.001 | Example only: Directorate Meeting | 2024-01-05 | closed | 2024-02-20 | Full communications plan not needed for this project - -Light version only | SRO | Agreed | 2024-02-19
D.002 | Example only: Supplier meeting | 2024-03-02 | open | 2024-03-21 | Methology the change KPI measure - no material difference | Project Board
D.003
D.004
D.005
D.006 | [8 empty] | Risk
D.007
D.008
D.009 | [8 empty] | Open
D.010 | [8 empty] | Complete
D.011
D.012
D.013
D.014
D.015
D.016
D.017
D.018
D.019
D.020
D.021
D.022
D.023
D.024
D.025
D.026
D.027
D.028
D.029

## Actions
Date updated: |  | Action Log
Action ID | Action | Start Date | End Date | Owner | Risk | Status | Notes
ACT.001 | Illustrative example only PM to keep updates via highlight reports; timetable to be used as reminder tool | date |  | Contract Manager | link to risk | delayed
ACT.002 | [5 empty] | on track
ACT.003
ACT.004
ACT.005
ACT.006
ACT.007
ACT.008
ACT.009
ACT.010
ACT.011

## DropDown Lists (hidden)
Risk ratings
1
2
3
4
5